## Sheet2
Tasks | 28th aug | 29th aug | 30th aug | 31st aug | 1st sept | 2nd sept | 3rd sept | 4th sept | 5th sept | 6th sept | 7th sept | 8th sept | 9th sept
T2 | T2, 8-9 hours, Akshay G,Akshay R,Yash Lamba,Deepanker Aggarwal
T3 | T3,30 min,Soumya Vardhan Singh
T4 | T4,3-4 hours,Akshay Gupta, Paritosh Mittal, Abhishek Gupta
T1 |  | T1,6-7 hours,Vinayak Chopra, Aishwarya Jain
T5 |  | T5,8-9 hours,Deepanker Aggarwal, Soumya Vardhan Singh, Vinayak Chopra
T6 |  |  |  |  | T6,7-8 hours,Akshay Gupta, Paritosh Mittal, Abhishek Gupta, Aishwarya Jain
T7 | [5 empty] | T7,1 hour,Akshay Rajvanshi,Yash Lamba
T8 | [6 empty] | T-8,10-12 hours,Akshay Rajvanshi,Yash Lamba, Soumya Singh,Vinayak Chopra,Aishwarya Jain
T9 | [8 empty] | T-9,15-18 hours,Entire Group
T10 | [9 empty] | T10,5-6 hours,Akshay Rajvanshi, Yash Lamba, Deepanker Aggarwal
T11 | [11 empty] | T11,4 hours,Abhishek Gupta, Soumya Singh

## Sheet1
Task Id | Task Name | Start Date | Duration | End Date | Who | Dependency | % Completion
T1 | Creating Project Logo | 2012-08-29 | 6-7 hours | 2012-08-30 | Vinayak Chopra, Aishwarya Jain | 0 | 0
T2 | Creating questionairre for admin to understand workflow | 2012-08-28 | 8-9 hours | 2012-08-29 | Akshay Gupta | 0 | 0
Akshay Rajvanshi
Yash Lamba
Deepanker Aggarwal
T3 | Taking Appointment from Mr. Anoop, Mr. Ajay, Mr. Amit and Ms. Suruchi | 2012-08-28 | 30 min | 2012-08-29 | Soumya Vardhan Singh | T2 | 0
T4 | Meeting with Mr. Anoop - Regarding Research grants | 2012-08-28 | 3-4 hours | 2012-08-31 | Akshay Gupta, Paritosh Mittal, Abhishek Gupta | T3 | 0
| Meeting with Mr. Ajay - Regarding buying Equipments | 2012-08-28 | 3-4 hours | 2012-08-31 | Akshay Gupta, Paritosh Mittal, Abhishek Gupta | T3 | 0
| Meeting with Mr. Amit - Regarding finances | 2012-08-28 | 3-4 hours | 2012-08-31 | Akshay Gupta, Paritosh Mittal, Abhishek Gupta | T3 | 0
| Meeting with Ms. Suruchi - Regarding finances | 2012-08-28 | 3-4 hors | 2012-08-31 | Akshay Gupta, Paritosh Mittal, Abhishek Gupta | T3 | 0
T5 | Brain-Storming on UI - (design , possible features) | 2012-08-29 | 8-9 hours | 2012-09-02 | Deepanker Aggarwal, Soumya Vardhan Singh, Vinayak Chopra |  | 0
T6 | Creating questionairre for meeting with End - Users (Faculty) | 2012-09-01 | 7-8 hours | 2012-09-02 | Akshay Gupta, Paritosh Mittal, Abhishek Gupta, Aishwarya Jain | T4 | 0
T7 | Taking Appointment from Faculty | 2012-09-02 | 1 hour | 2012-09-05 | Akshay Rajvanshi, Yash Lamba | T6 | 0
T8 | Meeting with entire Faculty (for understanding feature requirement) | 2012-09-03 | 10 - 12 hours | 2012-09-06 | Akshay Rajvanshi,Yash Lamba, Soumya Singh,Vinayak Chopra,Aishwarya Jain | T7 | 0
T9 | Brain Storming on Software WorkFlow | 2012-09-05 | 15-18 hours | 2012-09-08 | Entire Group | T4,T8 | 0
T10 | Prioritizing WorkFlow Elements | 2012-09-06 | 5-6 Hours | 2012-09-08 | Akshay Rajvanshi, Yash Lamba, Deepanker Aggarwal | T9 | 0
T11 | Programming on highest Priority Element | 2012-09-08 | 4 hours | 2012-08-09 | Abhishek Gupta, Soumya Singh